NEWFIELD SCHOOL

## School Development Plan

2022 – 2023

The SDP process at Newfield School: An integrated framework for continued improvement

SLT identify issues that need prioritising

Ongoing

Issues highlighted in consultation with SIP

Termly

Analysis of end of year summative tracking data

July

Governing Body

Termly

Analysis of termly tracking data

Termly

SDP

Written by HT in consultation with DHT’s. Identifies prioritised areas for development with measurable learning outcomes. SDP communicated to all staff.

Early Sept

Appraisal process for all staff will address issues relevant to SDP

By Oct half-term

Interim review of SDP

Termly

End of year evaluation of SDP.

This informs the SEF. Areas for further development identified.

July

Action Plans 2022-23

- All action plans run from September 2022 to Sept 2023.

- A range of staff contribute to the delivery of this overall action plan as per their responsibilities within school and they have their own plans to achieve this

- The HT and DHT’s will review this SDP termly (in December, March and July).

Progress in meeting each target is summarised in the final column. The following RAG colour coding is used:

|  | Achieved |
| --- | --- |
|  | On target – strategies have begun, more work to be done |
|  | Not yet addressed |

Summary of Priorities 2022-2023

| AREA | Objectives |
| --- | --- |
| Quality of Education (CW/IG/SF) | - INTENT - To review current assessment systems and research alternatives. - To ensure additional funding is used effectively and secures improvements for disadvantaged pupils (separate plan also). - Consolidate the Remote education offer for all pupils which leads to appropriate outcomes for successful transition return or to next steps - IMPLEMENTATION - Enhance teacher’s subject knowledge and expertise through allegiance and links with other schools - All pupils to be identified early for intervention (both academic and non-academic and all interventions are evaluated and impact evidenced. - Subject coordinators reporting is consistent and self-evaluation of their subjects drives developments. - To consolidate a whole school approach to improve literacy and numeracy. - To develop staff knowledge and practice in utilising TA support within the classroom - To improve pupils reading ability to enable them to access a full curriculum and external examinations - IMPACT - To ensure appropriate outcomes (in relation to starting points) for all pupils, particularly end of KS4 through external accreditation results- both academic and vocational. - To develop and ensure appropriate experiences are evidenced through schools discrete curriculum of personal development |
| Leadership and Management (CW) | - Safeguarding is effective at all times - To Enhance governor involvement and understanding of school. - To continue to develop parental engagement. - To deliver additional therapies offered by school which will improve the offer |
| Behaviour and Attitudes (SF) | - To provide opportunities to experience real life situation through the school passport and ensure that tracking and evidence supports the work completed - To develop a whole school approach to dealing with local issues that may affect all pupils - To support staff knowledge and understanding of working with increasing number of ASD pupils |
| Personal Development (IG) | - To continue to develop the mental health agenda and wellbeing across the school - To Enhance links with the community to provide experiences to develop pupils personally and socially through SMSC programme. - To utilise assessments to demonstrate ‘impact’ of PSHE teaching and learning in your school. |

QUALITY OF EDUCATION (SLT Responsibility CW,SF)

INTENT

| Target | Impact | Strategies | Timescale | UPDATE |
| --- | --- | --- | --- | --- |
| To review current assessment systems and research alternatives | Ensure that School has an assessment system that continues to track progress, however is functionally improved to aid efficiency of reporting and analysis and adequate to track an increasingly broader curriculum | - Assess the need for change - Research systems used by other schools - Consult with SIMS over capacity for changes Consult with SLT and formulate implementation plan | Oct 2022 Oct and ongoing Jan 2022 Mar 2022 |  |
| To ensure additional funding is used effectively and secures improvements for disadvantaged pupils (separate plan also). | All pupils to make at least expected progress in English and Maths across all Key Stages All pupils to make good or better progress in reading. All Key Stage 4 pupils to leave with a minimum of 5 external outcomes. All pupils have access to quality remote learning experience. Improvements in the attendance and behaviour of all PP pupils. Improvement in pupils mental, emotional and physical health Peer Mentors provide an accessible point of contact for their peers who are experiencing difficulties in school. Staff develop phonics knowledge. To provide CPD to help support staff with teaching the new PSHE curriculum Evidence PP data, objectives and impact PP meeting minutes Intervention data Progress data | - SLT (SF) to oversee additional funding expenditure - Whole school CPD training in supporting pupils with academic and non-academic areas - Regular meetings between SLT and to review additional funding - Gov (RH ) to meet with SF to challenge impact of additional spending | Oct 2022 on-going half termly |  |
| Consolidate the Remote education offer for all pupils which leads to appropriate outcomes for successful transition return or to next steps | Ensure pupils who are absent from school for any length of time have access to the curriculum in order to maintain progress All pupils are educated and school works closely as part of a multi agency approach to ensure continual safeguarding is in place and education is adapted with a view to progressing to full return Evidence Remote learning resources Remote learning logs Progress Data Tutor records Minutes of mutli-agency meetings | - All pupils to be set up with home learning email addresses or have access to printed resources - Home learning packs in line with their current curriculum prepared and ready - Arrangements for contact and virtual processes in place - All teachers to document engagement of class in any home learning - All tuition is tracked and monitoring - All pupils are safeguarded and monitored | Sept 2022 Sept 2022 Sept 2022 Sept 2022 Sept 2022 and ongoing |  |

IMPLEMENTATION

| Target | Impact | Strategies | Timescale | UPDATE |
| --- | --- | --- | --- | --- |
| Enhance teachers subject knowledge and expertise through allegiance and links with other schools | To develop knowledge and skills in teaching of non-specialist subjects in order to enhance the curriculum for all pupils Evidence CPD Records Subject Coordination files Planning Perf mgt reviews | Facilitate teachers to link with other schools with a focus on particular subjects Teachers given access to CPD opportunities and schedule dissemination to other staff Use external advisors and associations for focussed support | Sept 2022 and ongoing |  |
| All pupils to be identified early for intervention (both academic and non-academic and all interventions are evaluated and impact evidenced. | Intervention for all pupils is tracked, monitored and evaluated in a timely fashion Interventions identified make a difference to the progress of pupils Evidence Data and internal tracking Planning Intervention documentation Intervention reports Perf mgt reviews | - Interventions identified to support pupils - All support staff target is inputting onto system interventions for pupils - Termly data to inform interventions - SIMS utilised for tracking of Interventions and monitored by SLT - Memebr of staff timetabled for additional interventions - reviewed half termly | Termly Termly Termly Termly Ongoing |  |
| Subject coordinators reporting is consistent and self-evaluation of their subjects drives developments. | Subject coordinators is reported consistently across school and can provide evidence to support a sustained development for their subject area Subject coordinators can discuss with confidence and share information about their subject Evidence: Performance Management Work scrutiny Moderation Termly data Subject Progress Report Self – Evaluation of subject Evaluation of Subject coordination Evidence | - All teachers to have a subject coordination responsibility as part of perf mgt and in line with their pay scale - Subject coordinators to attend any relevant training which enhances their knowledge of coordination - Subject coordinators to keep abreast of developments within their subject through associations and directed time to be focussed on self CPD - SC’s maintain their standardised folders keep it updated evidentially – timetables in directed time cycle - SLT to monitor via interim reviews - Line management meetings | Sept 2022 On-going On-going Half termly |  |
| To Consolidate a whole school approach to further improve literacy and numeracy. | Both literacy and numeracy are a prominent and visual aspect throughout school and pupils develop across all key stages and raise their standards in English and Maths Evidence Subject Coordinators folders Literacy / numeracy analysis reports Progress Data | - To focus on a different area each half term and for all staff to understand and focus on it. - To feedback to all staff on a termly basis during staff meeting time - To provide SLT with a termly report | Sept 2022 Termly Termly |  |
| To develop staff knowledge and practice in utilising TA support within the classroom | Better utililisation and deployment of classroom TA'’ will benefit all pupils and will create a helathire and more enagaging learning environment, which is better for both staff and pupils. Evidence CPD records Learning walks / drop ins Termly data Intervention records | - Training with all staff on best use of TA - Protocol agreed for communication between teacher and TA - Dedicated time to review in class practices andplan adaptations where necessary - Feedback – sharing of ideas and impact within the classroom | Jan 2022 Feb 2022 Jan 2022 May 2022 |  |
| To improve pupils reading ability to enable them to access a full curriculum and external examinations | Improved skills in reading by all pupils Pupils read for pleasure across school Pupils read at chronological age Pupils read widely, and often across all subjects to a high standard Evidence Reading age results Pupil progress data Teachers planning Displays | - Learning mentors baseline and assess all pupils twice yearly - Daily Interventions are in place and monitored (EW) - Coordinator for delivery of phonics programme - Resources to facilitate enjoyment and learning are available - Reading monitored by CR/DD as part of coordination responsibility | Sept 2022 and on-going Termly On-going |  |

IMPACT

| Target | Impact | Strategies | Timescale | Update |
| --- | --- | --- | --- | --- |
| To ensure appropriate outcomes (in relation to starting points) for all pupils, particularly end of KS4 through external accreditation results- both academic and vocational. | Personalised curriculum for all pupils to achieve and gain accreditation to support transition. To develop a broad and balanced curriculum that meet pupil’s individual needs and they achieve. Any subject specific curriculum or assessment issues are addressed in subject progress reports October and March and necessary interventions are put in place Evidence: End of term / yearly progress data Subject coordination folders Accreditation results Subject progress reports Intervention reports and impact | - DHT to highlight underperforming pupils and/or groups of pupils in termly data analysis - Subject Coordinators to address identified issues within their subject progress reports and annual subject reviews. - Any remedial action put in place – SLT - Alt Prov co-ordinator to review and monitor pupils gaining of external accreditation - Annual Reviews of EHCP - Interventions to be timely, effective, tracked and evaluated . | Termly Twice yearly On-going Termly On-going on-going |  |
| To develop and ensure appropriate experiences are evidenced through schools discrete curriculum of personal development | All pupils to experience, achieve and gain recognition in personal development activities outside of the academic curriculum Evidence: Subject coordination folders (PSHE) Passport tracker Personald development certificates / results | - Subject Coordinators and class teachers to organise activities and experiences that supports pupils personal development - Experiences are tracked so all pupils have involvement - Awards are celebrated . | Sept 2022 Ongoing Ongoing |  |

LEADERSHIP AND MANAGEMENT (SLT Responsibility CW)

| Target | Impact | Strategies | Timescale | UPDATE |
| --- | --- | --- | --- | --- |
| Safeguarding is effective at all times | Safeguarding is very secure, reporting and impact demonstrates this CPOMS is fully utilised by all staff for record keeping and communicating Evidence Safeguarding data CPOMS usage Staff training Governor link meetings | - CW meet with safeguard gov termly - All staff to competently use the system for reporting incidents and understand the importance –addressed in staff meeting and reminded at regular intervals - Safeguarding leads to review procedures half termly - Governor training identify / monitored | termly on-going Half termly Sept 2022 and on-going |  |
| To enhance governor involvement and understanding of the school | Gov body to develop their roles and understanding of school to help drive school improvement Evidence Gov minutes of meetings Gov visits Gov timetable for year Gov action plan | - Sub-groups Termly meeting with school staff and SLT to focus on identified areas - Gov vists to school are regular and gov feedsback at FGB meetings - Gov action plan to be discussed and updated at each FGB meeting | Termly Ongoing Termly |  |
| To continue to develop parental engagement | The school has highly successful strategies for engaging with parents to the benefit of pupils, including those who find working with the school difficult. Website use as a communication method Termly newsletter distributed Evidence Parent survey Safeguarding data SMSC evidence Parental consultation day Annual Reviews Coffee Mornings | - Signpost and offer parenting courses and family learning sessions throughout the year - UPS3 teacher responsibility as part of whole school contribution - Invite and provide transport to any opportunities for parents to visit, e.g., productions / annual reviews - Attend all Multi-agency meetings. - Develop relationships with parents to encourage and support learning - Develop parental opportunities to be involved in developing core skills with pupils | on-going Sept 2022 On-going On-going On-going On-going |  |
| To deliver additional therapies offered by school which will improve the offer | To build on existing therapeutic intervention and increase schools offer for identified pupils to support their progress Evidence Proposal to LA for SALT/OT on site Art therapy impact of intervention Mable therapy impact of interventions Creative Balance impact of interventions | - Review of timetables to deliver therapeutic input from existing staff with experience - Develop a timetable of interventions for pupil (s)to be supported as part of CAHMS student placement who will work directly with school - Liaise with the MHST to deliver and identify support - To meet half-termly with Mental Health lead to interventions and therapy offers | Sept 2022 Oct 2022 Oct 2022 Half-termly |  |

BEHAVIOUR AND ATTITUDES (SLT Responsibility SF)

| Target | Impact | Strategies | Timescale | UPDATE |
| --- | --- | --- | --- | --- |
| To provide opportunities to experience real life situation through the school passport and ensure that tracking and evidence supports the work completed | Pupil development improved. Development of pupils as citizens Evidence Trip evaluations and feedback (written and photograph) Work experience tracking and feedback Link to SMSC school passport | - SMSC coordinator to list ideas and activities locally - SMSC to monitor passports - Develop relationship with local businesses (e.g. Plaza cinema) - KS4 pupils DofE programme - Work with Sefton EBP to identify appropriate placements early for work experience. - Extend work experience if applicable for some - Visiting speakers to attend school - Provide opportunities for pupils to know about the local area and community - All pupils to work towards the pledges for positive experiences - Pupils to engage in work and activities off-site at school allotment | Sept 2022 termly on-going Sept 2022 On-going On-going On-going On-going On-going |  |
| To develop a whole school approach to dealing with local issues that may affect pupils | Pupils will develop the knowledge, skills and attributes they need to stay safe and develop healthy relationships and to manage their lives within their local communities, now and in the future. Evidence PSHE / RSHE Curriculum Subject coordinator reports External visitors feedback | - Visiting speakers to attend school to provide workshops for high profile local issues – knife and gun crime, - Provide opportunities for pupils to know about the local area and community and signpost them for activities - Communicate work with local agencies to identify and target support where needed | Sept 2022 and ongoing Sept 2022 and ongoing |  |
| To support staff knowledge and understanding of working with increasing number of ASD pupils | Staff will be supported in refreshing and in some cases developing their knowledge and understanding of working with pupils with an ASD diagnosis Evidence CPD records Staff feedback ASEN register | - All staff to undertake the Autism Education trust course for making sense of Autism and also Schools good Autism practice - Review resources which supported the 8 principles of good autism practice - Feedback to staff changes made | Sept 2022 and ongoing Mar 2022 May 2022 |  |

PERSONAL DEVELOPMENT (SLT Responsibility CW/SF)

| Target | Impact | Strategies | Timescale | UPDATE |
| --- | --- | --- | --- | --- |
| To continue to develop the mental health agenda and wellbeing across the school | Staff and pupils are aware and have strategies for supporting mental health concerns Intervention, support and appropriate curriculum is in place to continue work in the area of mental health Evidence CPD Minutes of meetings Interventions for identified pupils Mental Health reports from EW OH referrals Work and support from MHST | - Mental health training as part of whole school CPD, - HT to meet with EW – UPS whole school significant contribution to develop mental health awareness and measuring impact - HT and EW to meet with MHST practionitioner - Signposting and developing relationships with outside agencies - Complete and evidence mental health standards against the Anna Freud framework | Termly Termly on-going |  |
| To enhance links with the community to provide experiences to develop pupils personally and socially through SMSC programme. | Pupil development improved. Development of pupils as citizens Evidence Trip evaluations and feedback (written and photograph) Work experience tracking and feedback | - SMSC coordinator to list ideas and activities locally - SMSC to monitor passports - Develop relationship with local businesses (e.g. Plaza cinema) - KS4 pupils DofE programme - Work with Sefton EBP to identify appropriate placements early for work experience. - Extend work experience if applicable for some - Visiting speakers to attend school - Provide opportunities for pupils to know about the local area and community - All pupils to work towards the pledges for positive experiences - Pupils to enagage in work and activities off-site at school allotment | Sept 2022 termly on-going Sept 2022 On-going On-going On-going On-going On-going |  |
| To utilise assessments to demonstrate ‘impact’ of PSHE teaching and learning in your school. | Effective assessment allows pupils and teachers to reflect on what has been learned, increases motivation for future learning and demonstrates impact. Evidence CPD record Assessment records and progress | - PSHE coordinator to get bespoke advice from PSHE association on how to implement pupil and teacher-friendly assessment methods in your school. - Class teachers to assess and monitor progress of individuals PSHE | Oct 2022 Termly |  |

Other significant developments during Term 1